## Sprint1
Date : Feburary 26th - March 11 (Sprint 1)
Meet days: Wednesday, Saturday
Developer | What tasks did I work on / complete? | What am I planning to work on next? | What tasks are blocked waiting on another team member?
Shireesh | Designed the initial database schema for courses, faculty, and students in SQL. Created the UML diagram for the project. Set up the environment for database management using AWS RDS and SQL Workbench. Conducted a thorough analysis of faculty needs and requirements. | Start working on the faculty modules | N/A
Ashish | Researched and selected technologies for cloud setup and authentication methods, focusing on AWS and JWT strategies. Began designing basic student APIs with a focus on simple functionalities like logging in and viewing profiles. | Start implementing the authentication service and initial student APIs based on the research findings. | N/A
Vinay | Researched student user needs and behaviors to inform the design of student APIs. Created UI wireframe design for all the modules using Figma. Created a mockup login , student interface, dashboard designs.Created the initial structure for project documentation. | Continue with the UI design, work on the student modules after the feedback from the teammates | The initial feedback cycle for wireframes took longer than expected.
Lekhana | Led the initial setup of cloud infrastructure,defining IAM roles and policies. Started drafting admin APIs by outlining key administrative functionalities. Collaborated with the team to ensure alignment with backend functionalities. | Start working on the admin api and backend functionalities | N/A

## Sprint2
Date : March 12- March 25 (Sprint 2)
Meet days: Wednesday, Saturday
Developer | What tasks did I work on / complete? | What am I planning to work on next? | What tasks are blocked waiting on another team member?
Shireesh | Developed APIs for faculty to view a homepage listing their current and previous courses. Integrated this feature with MySQL to handle both published and unpublished courses.Implemented APIs for adding syllabus content, assignments, quizzes, and posting announcements. Set up endpoints to view and manage grades and student lists for each course. | Begin developing APIs for adding syllabus content and managing assignments.Continue refining these features and start integrating feedback mechanisms into the course management system. | Challenges in ensuring data consistency across different course management features.
Ashish | Developed APIs for students to view their enrolled courses, including details on published content. Used Node.js and Express to connect with MySQL, ensuring efficient data retrieval. Focused on refining and testing the APIs for viewing course content. Ensured robust error handling and response formatting for better frontend integration. | Start implementing student API endpoints for setting profile information and notifications.Prepare to expand the functionalities to include interactions with quizzes and assignments. | Minor issues with API response times due to database query inefficiencies
Vinay | Enhanced the UI design for viewing quizzes and assignments, integrating feedback from initial user tests to improve usability and accessibility.Developed interactive components for students to view their grades and manage their profile settings using React. Conducted integration tests with backend APIs. | Focus on polishing the user experience and preparing for a comprehensive presentation of the updated student interface. | Some challenges in syncing frontend updates with backend data updates.
Lekhana | Started with the React UI design and created a base template for the admin . Divided the Course faculty and other modules and the css. Added some functionalities to it . Redesigned it after the feedback from the teammates and followed a base template for the design of all the UI | Begin developing features for admins to view comprehensive student lists for each course.Start implementing the admin backend and routig it and refine IAM configurations based on comprehensive security requirements. | N/A

## Sprint3
Date : March 26- April 8 (Sprint 3)
Meet days: Wednesday, Saturday
Developer | What tasks did I work on / complete? | What am I planning to work on next? | What tasks are blocked waiting on another team member?
Shireesh | Finalized the APIs for faculty to manage assignments, quizzes, and grades. Ensured that all endpoints are secure and optimized for performance.Conducted extensive testing on faculty features, identifying and fixing bugs in assignment submission and grade posting processes. Prepared detailed API documentation for faculty functionalities. | Begin comprehensive testing of all faculty APIs with mock data and simulate real-world usage scenarios.Start preparing for deployment by setting up automated deployment scripts and finalizing cloud infrastructure configurations. | Some issues with data synchronization in grade posting under high load.
Ashish | Developed advanced functionalities for students to interact with quizzes and assignments. Developed and tested enhancements for student APIs related to viewing and interacting with course content. Focused on optimizing database queries to improve response times. | Start the deployment on cloud and create the infrastructure and integrating all modules | Waiting others to complete the modules as we need to proceed for deployment on EC2
Vinay | Helped shireesh with faculty modules and worked on the student modules (Add notification settings for Students)mainly testing the modules with test cases and troubleshooting for any issues. | Help with the deployment and work on documentation related to ui frameworks testcases and other sort | NA
Lekhana | Worked on the backend and integrating the database to the frontend to get the real time data. Fetching the data and setting few other issues that were needed to be resolved | Begin developing features for admins to view comprehensive student lists for each course.Start implementing the admin backend and routig it and refine IAM configurations based on comprehensive security requirements. | N/A

## Sprint4
Date : April 8- April 22 (Sprint 4)
Meet days: Wednesday, Saturday
Developer | What tasks did I work on / complete? | What am I planning to work on next? | What tasks are blocked waiting on another team member?
Shireesh | Finalized all the modules and worked on integration of the modules. | Conduct thorough testing of the entire system. Debug and fix issues from testing.Make final tweaks and improvements based on testing feedback. | NA
Ashish | Deploy APIs and database to AWS with Auto Scaling and Load Balancer.Worked on integration of all the modules with shireesh. | Start the deployment on cloud and create the infrastructure and integrating all modules | NA
Vinay | Conducted intermediate testing of all functionalities.Implemented advanced API features based on feedback.Performed comprehensive system testing. | Will have to work on documentation | NA
Lekhana | Finalized all modules and tested on RDS. Testing it in the enviornment and passed it to shireesh and ashish. Helped them with integration part | Begin developing features for admins to view comprehensive student lists for each course.Start implementing the admin backend and routig it and refine IAM configurations based on comprehensive security requirements. | NA

## Sprint5
Date : April22 - May 6 (Sprint 5)
Meet days: Wednesday, Saturday
Developer | What tasks did I work on / complete? | What am I planning to work on next? | What tasks are blocked waiting on another team member?
Shireesh | Deployed the frontend on a EC2 instance and Tested the whole system if its working or not.Finalized everything | Final presentation | NA
Ashish | Deplyed backend on a EC2 instance and test every module is working fine | Final presentation | NA
Vinay | Completed the documentation and helped other teammembers | Final presentation | NA
Lekhana | Completed the documentation and helped other teammembers | Final presentation | N/A